## Standalone Micro-Scale Scheme
Annex AE - Standalone Micro-Scale Scheme Rules
External Inputs |  |  | GS Carbon + Sustainability Track |  |  |  | Documents & Deliverables | Reference
I. Listing
|  |  | Project conceptualisation (≤10,000 t CO2) |  |  |  |  | Micro-Scale Scheme Rules Section 1 & 2
I.a |  |  | a. Project Design (Regular Project Cycle) |  |  |  |  | Micro-Scale Scheme Rules Section 3
Comments by Stakeholders |  |  | Conduct Local Stakeholder Consultation (live meeting) |  |  |  |  | Toolkit chapter 2.6
|  |  | Submit simplified PDD to GS (Time of first submission to GS) |  |  |  | Simplified PDD | Section A & D of Simplified PDD
LSC reporting review by GS
Request for further clarification from GS (if any)
|  |  | Project is Listed |  |  |  | Final LSC reporting (in simplified PDD), LSC Review document(s), Project Listed
OR
I.b |  |  | b. Project Design (Retroactive Project Cycle) |  |  |  |  | Micro-Scale Scheme Rules Section 3
|  |  | Upload draft simplified PDD |  |  |  | Draft Simplified PDD | Separate template
|  |  | PFA invoice raised by GS |  |  |  |  | Annex L
PFA fee paid by PP
|  |  | i. Regular PFA |  | ii. Fast-track PFA
|  |  | PFA by GS |  | Signing of MoU by GS and PP
2-hour consultation between GS & PP
|  |  | Project is Listed |  |  |  | Simplified PDD, PFA document, Project Listed
II. Validation and Registration | [7 empty] | Micro-Scale Scheme Rules Section 9
|  |  | Validation Fees invoice generated by Gold Standard Registry |  |  |  |  | Fee structure: Micro-Scale Scheme Rules Section 9
Validation Fees paid by PP
Sustainable Development Assessment by Objective Obsever at Validation Level
II a. |  | a. | If Objective Observer (OO) is appointed
|  |  | OOs recommended by PP |  |  |  |  | Micro-Scale Scheme Rules Section 11
OO is appointed by GS
Site-visit by OO
|  |  | SD Assessment by OO |  |  |  | Draft Gold Standard Sustainable Development Appraisal Report - Validation Stage
Request for clarification by OO to PP
Appraisal Report submitted by OO(s) to GS for review
Request for clarification by GS to OO
|  |  | GS Sustainable Development Appraisal Report submitted to GS |  |  |  | Final Gold Standard Sustainable Development Appraisal Report - Validation Stage
II b. |  | b. | If Objective Observer is not appointed |  |  |  |  | Micro-Scale Scheme Rules Section 11
|  |  | Self SD assessment by PP in the GS Sustainable Development Appraisal Report - Validation Appraisal |  |  |  | Gold Standard Sustainable Development Appraisal Report - Validation Stage
|  |  | Upload simplified PDD, ER calculation sheet, draft GS Sustainable Development Appraisal Report by PP onto GS Registry |  |  |  | Simplified PDD, GS Sustainable Development Appraisal Report (by PP/OO) - Validation Stage
II.A |  | A. | External validation by DOE
Comments by Stakeholders & GS NGO Supporters |  |  | SFR in progress (at least 60 days and/or live meeting) |  | Upload validation workplan (by DOE only) |  | Validation Workplan by DOE | SFR: Toolkit Chapter 2.11 DOE workplan: Toolkit Chapter 3.3
Validation of activity by DOE
Upload Final PDD, ER calculation sheet, Validation Report, GS SD Appraisal Report etc. onto GS Registry
Comments by TAC & GS NGO Supporters |  |  | 8-week registration review period by GS
Request for further clarification from GS (if any)
|  |  | Project is registered with GS |  |  |  | Final PDD, ER calculation sheet(s), DOE Validation Report(s), Final GS Sustainability Appraisal Report (by PP/OO) - Validation Stage, 8-week registration review document; Project Registered
OR
II.B |  | B. | Internal validation by GS
Comments by Stakeholders & GS NGO Supporters |  |  | SFR in progress (at least 60 days and/or live meeting) |  | Validation of activity by GS |  |  | SFR: Toolkit Chapter 2.11
Upload Final PDD, ER calculation sheet, GS SD Appraisal Report by PP, etc. onto GS Registry
Comments by TAC & GS NGO Supporters |  |  | 8-week registration review period by GS
Request for further clarification from GS TAC and NGO Supporters
|  |  | Project is registered with GS |  |  |  | Final PDD, ER calculation sheet(s), Internal Validation Protocol, Final GS Sustainability Appraisal Report (by PP/OO) - Validation Stage, 8-week registration review document; Project Registered
IV. Verification and issuance
|  |  | Upload monitoring report, ER calculation sheet(s) to Registry |  |  |  | Draft Monitoring report, ER calculation sheet, GS Sustainable Development Appraisal Report - Verification Stage | Micro-Scale Scheme Rules Section 10
|  |  | Verification Fees invoice generated by Gold Standard Registry (annually) |  |  |  |  | Fee structure: Micro-Scale Scheme Rules Section 10
Verification Fees paid by PP (annually)
IV.a |  | a. | External verification by DOE |  |  |  |  | Micro-Scale Scheme Rules Section 10
|  |  | Upload verification workplan(s) for project |  |  |  | Verification workplan by DOE | Toolkit Chapter 4.4
Verification by DOE including site-visit
|  |  | Upload revised Monitoring Report, GS SD Appraisal Report - Verification Stage, ER calculation sheet(s), Verification Report onto the GS Registry |  |  |  | Monitoring Report(s), ER calculation sheet(s), Verification Report(s), GS Sustainable Development Appraisal Report - Verification Stage
Comments by TAC & GS NGO Supporters |  |  | 3-week issuance review period by GS
Request for clarification from GS (if any)
|  |  | Issuance of VERs |  |  |  | Monitoring Report(s), ER calculation sheet(s), Verification Report(s); GS Sustainable Development Appraisal Report - Verification Stage, VERs Issued
OR
IV.b |  | b. | Internal verification by GS |  |  |  |  | Micro-Scale Scheme Rules Section 10
|  |  | i. No OO is appointed |  |  | ii. OO is appointed |  | Micro-Scale Scheme Rules Section 11
|  |  | PP submits self assessed GS Sustainable Development Appraisal Report - Verification Stage and Monitoring Report |  |  | OO submits GS Sustainable Development Appraisal Report (Refer step II a. above) and PP submits Monitoring Report | Draft Gold Standard Sustainable Development Appraisal Report - Verification Stage, Monitoring Report
|  |  | Verification of the carbon and sustainibility aspects by GS |  |  | SD Appraisal Report submitted by OO and GS does a verification of carbon aspects
|  |  | Upload revised Monitoring Report(s), GS Sustainable Development Appraisal - Verification Report, ER calculation sheet(s), onto the GS Registry |  |  |  | Monitoring Report(s), ER calculation sheet(s), Final Gold Standard Sustainable Development Appraisal Report - Verification Stage, Internal Verification Protocol
Comments by TAC & GS NGO Supporters |  |  | 3-week issuance review period by GS
Request for further clarification from GS TAC and NGO Supporters
|  |  | Issuance of VERs |  |  |  | Monitoring Report(s), ER calculation sheet(s), Gold Standard Sustainable Development Appraisal Report - Verification Stage, Internal Verification Protocol; VERs Issued
Flowchart Key
Action by TAC and GS NGO Supporters
Action by The Gold Standard
Action by PP/DOE
Documents and Deliverables