## PoA project cycle
ANNEX AG - GS PoA Project Cycle
External Inputs |  | GS PoA Carbon + Sustainability Track |  |  |  | Documents & Deliverables | Reference
I. Listing of Programme
Program conceptualisation
Comments by Stakeholders |  | Conduct Design Consultation at PoA level |  |  |  |  | Annex F section 6
|  | Submit Design Consultation Report to GS (Time of first submission to GS) |  |  |  | Design Consultation Report
Design Consultation Report review by GS
|  | Identify CPA/VPA (per technology/methodology; CPA/VPA(x), CPA/VPA(y)…..) |  |  |  |  | Annex F section 8
I.a |  | a. If CPA(s)/VPA(s) is/are through the Regular Project Cycle |  |  |  |  | Annex F section 3.3 & 3.4
Comments by Stakeholders & GS NGO Supporters |  | LSC at CPA/VPA level (Live only) |  |  |  |  | Toolkit chapter 2.6
|  | Upload LSC meeting report(s) on the GS Registry |  |  |  | LSC report(s) for CPA(s)/VPA(s)
LSC report(s) - review by GS
Request for further clarification from GS (if any)
|  | PoA & CPA(s)/VPA(s) Listed |  |  |  | Final LSC report(s), LSC review document(s), PoA Listed on Registry
AND/OR
I.b |  | b. If CPA(s)/VPA(s) is/are through the Retroactive Project Cycle |  |  |  |  | Annex F section 3.3 & 3.4
Upload draft PoA-DD, CPA/VPA-DD(s), GS PoA-Passport, GS CPA/VPA-Passport(s)
|  |  |  | PFA invoice raised by GS |  |  | Annex L
PFA fee paid by PP
PFA by GS
|  | PoA & CPA(s)/VPA8s) Listed under GS |  |  |  | PFA document(s), PoA Listed
II. Validation and Registration of Program
|  | Upload Draft PoA-DD, CPA/VPA-DD(s), GS PoA-Passport, GS CPA/VPA-Passport(s) etc on GS Registry for SFR & submit to DOE for validation |  |  |  | Draft PoA-DD, CPA/VPA-DD(s), GS PoA-Passport, GS CPA/VPA-Passport(s)
Comments by Stakeholders & GS NGO Supporters |  | SFR in progress (at least 60 days and/or live meeting) |  |  | Upload validation workplan (by DOE only) | Validation workplan by DOE | SFR: Toolkit Chapter 2.17 DOE workplan: Toolkit Chapter 3.3
[5 empty] | Validation of PoA & CPA/VPA(s) by DOE (per methodology/technology) |  | Annex F section 11
Upload Final PoA-DD, CPA/VPA-DD(s), GS PoA-Passport, GS CPA/VPA-Passport(s), ER calculation sheet(s), Validation Report(s) etc on GS Registry
Comments by TAC & GS NGO Supporters |  | 8-week registration review period by GS
Request for further clarification from GS (if any)
|  | PoA registered under GS |  |  |  | Final PoA-DD, CPA/VPA-DD(s), PoA-Passport, CPA/VPA-Passport(s), ER calculation sheet(s), DOE Validation Report(s), 8-week registration review document; PoA Registered
III. Inclusion of Activities (CPAs/VPAs)
Identify CPA(s)/VPA(s)
III.a If CPA/VPA is regular
III.a |  | a. If CPA(s)/VPA(s) is/are through the Regular Project Cycle |  |  |  |  | Annex F section 3.3 & 3.4
Comments by Stakeholders & GS NGO Supporters |  | LSC at CPA/VPA level (Live)** |  |  |  | **Multiple CPA(s)/VPA(s) can conduct single LSC meeting with separate LSC reports in separate accounts on GS Registry | Annex F section 6
|  | Open separate project account on GS Registry for each CPA/VPA |  |  |  |  | Annex F section 5
|  | Upload LSC meeting report on the GS Registry |  |  |  | LSC report for CPA/VPA
LSC report review by GS
Request for further clarification from GS (if any)
|  | CPA/VPA Listed (separately) |  |  |  | Final LSC Report, LSC Review Document, CPA/VPA Listed
OR
III.b |  | b. If CPA/VPA (s) is/are through the Retroactive Project Cycle |  |  |  |  | Annex F section 3.3 & 3.4
|  | Upload CPA/VPA-DD, GS CPA/VPA-Passport |  |  |  | CPA/VPA-DD, CPA/VPA-Passport
PFA invoice raised by GS
|  | PFA fee paid by PP |  |  |  |  | Annex F section 3.3 & 3.4
|  | i. Regular PFA |  |  | ii. Fast-track PFA
|  | PFA review by GS |  |  | Selection of fast track eligible DOE by PP |  | Fast track PFA rule
Signing of MoU by GS and PP
2-hour consultation between GS & PP (and DOE recommended)
|  | CPA/VPA Listed |  |  |  | CPA/VPA Listed
III. A Full Validation of Activities or Compliance Check by DOE during Inclusion
| A. | Full validation for Case 1 under section 3.4 of Annex F |  |  |  |  | Annex F section 3.4
|  | Upload VPA-DD, VPA-Passport, etc onto GS Registry for SFR & submit to DOE for validation |  |  |  | Draft VPA-DD, VPA-Passport
Comments by stakeholders & GS NGO Supporters |  | SFR in progress (at least 60 days and/or live meeting) |  |  | Upload validation workplan (by DOE only) | Validation workplan by DOE | DOE workplan: Toolkit Chapter 3.3
[5 empty] | Validation of VPA by DOE |  | SFR: Toolkit Chapter 2.17
Upload VPA-DD, VPA-Passport, ER calculation sheet, Validation Report etc on GS Registry
Comments by TAC & GS NGO Supporters |  | 8-week registration review period by GS |  |  |  |  | Annex F section 11
Request for further clarification from GS (if any)
|  | VPA included under PoA |  |  |  | Final VPA-DD, VPA-Passport, ER calculation sheet, Validation Report, CPA/VPA Registered
OR
| B. | Compliance check for Case 1 & 2 under section 3.3 and Case 2 under section 3.4 of Annex |  |  |  |  | Annex F section 3.3 & 3.4
|  | Upload CPA/VPA-DD, GS CPA/VPA-Passport, etc onto GS Registry for SFR & DOE compliance check |  |  |  | Draft CPA/VPA-DD, GS CPA/VPA-Passport
Review comments by stakeholders & GS NGO Supporters |  | SFR in progress (at least 60 days and/or live meeting) |  |  | Upload Inclusion workplan (by DOE only) | Incusion workplan by DOE
Compliance check by DOE
|  | Upload final CPA/VPA-DD, CPA/VPA-Passport, Inclusion report, ER calculation sheet |  |  |  | Revised CPA/VPA-DD, GS CPA/VPA-Passport, ER calculation sheet, Inclusion Report
Comments by TAC & GS NGO Supporters |  | 2-week compliance check period by GS |  |  |  |  | Annex F section 11
|  |  | +1 week review by GS (if selected for spot check, not mandatory) |  |  |  | Annex F section 11
Request for further clarification from GS (if any during spot check)
|  | CPA/VPA included under PoA |  |  |  | Final CPA/VPA-DD, GS CPA/VPA-Passport, ER calculation sheet, Inclusion Report, CPA/VPA Registered
IV. Verification and Issuance
|  | Submit monitoring report(s), ER calculation sheet(s) to DOE for all activities for which issuance is intended |  |  |  | Draft Monitoring Report(s), ER calculation sheet(s) | Annex F section 13
|  | Upload verification workplan(s) for activities selected for verification including site-visit |  |  |  | Verification workplan(s) by DOE | Toolkit Chapter 4.4
|  | Verification by DOE (including site-visit only for selected activities) |  |  |  |  | Annex F section 13
|  | Upload monitoring report(s), ER calculation sheet(s), verification report (only for selected activites) on the GS registry |  |  |  | Monitoring report(s), ER calculation sheet(s), Verification Report(s)
Comments by TAC & GS NGO Supporters |  | 3-week issuance review period by GS for all activities for which issuance is intended |  |  | + 3 weeks for spot checks based on target random approach (if activity selected) |  | Annex F section 13
Request for further clarification from GS (if any) for activities systematically verified
|  | Issuance of VERs or labelling of CERs for which issuance is intended |  |  |  | Monitoring Report(s), ER calculation sheet(s), Verification Report(s); CERs Labelled/VERs Issued
This flowchart entails the PoA cycle process from beginning to end, with the LSC (meeting) conducted at the activity level. Please refer to Annex F and Guidance Document for further information on conducting the LSC (meeting) at a PoA level.
Action by TAC and GS NGO Supporters
Action by Gold Standard
Action by CME/PP/DOE
Documents and Deliverables